## Sheet1
ID | Arquivo | Program & MY | PMT | Cost | Vendor Tooling | VO Tooling & Facilities | PDL Impact | CR | Change Title | ED&T | VO Labor Impact | Weight Impact | Owner | Approval Number | Part Number | Change Driver | TVM Binning | Reunião | Expected Outcome | Decision | Minutes
1 | 25CRF00388 - U625 25MY PP Mini Spare Wheel - PDL Update.xlsm |  | PMT 4 |  |  |  | Yes |  | U625 25MY PP J2 Mini Spare Wheel PDL Update |  |  |  | Lilian Fuscaldi | 25CRF00388 |  | (Non-Disc) NO BUILD – NB | Program
2 | 25CRF00389 (supersed 26CRF00073) - WAL MATERIAL CHANGE Jan 14th 1.xlsm | 25MY - U625 NA | PMT 1 | 7.14 |  |  | No | C14634137 | U625 WHEEL ARCH LINER MATERIAL CHANGE FROM FABRIC TO HARD PLASTIC |  |  | -1.814 | AFONTES9 | 25CRF00389 (supersed 26CRF00073) |  | (Disc) COST / COMPLEXITY REDUCT – CR | TVM
3 | 25CRF00390 - C14716423 U611 Cost only Update for LDM4.2.2 Rev3.xlsm | 25MY - U611 NA | PMT 1 | -1.25 |  |  |  | C14716423 | Update cost for LDM4.2.2 |  |  |  | SRASHADO | 25CRF00390 |  | (Non-Disc) CRITICAL TO WARRANTY – CW
3 | 25CRF00390 - C14716423 U611 Cost only Update for LDM4.2.2 Rev3.xlsm | 24MY - U611 China | PMT 1 | -1.52 |  |  |  | C14716423 | Update cost for LDM4.2.2 |  |  |  | SRASHADO | 25CRF00390 |  | (Non-Disc) CRITICAL TO WARRANTY – CW
4 | 25CRF00391 - U611 RC - PMT 800 Paint In-Source Black Painted Roof to capture cost save.xlsm | 25.5MY - U611 NA |  | 73.68 |  |  | Yes | TBD | CAP U611 Lincoln Aviator Black Painted Roof |  |  |  | Magdy Youssef (myousse9) | 25CRF00391 | MPC5J-1A330-AA | (Disc) COST / COMPLEXITY REDUCT – CR | TVM
5 | 25CRF00392 - Cost Only - C14746464 25.5MY RC U625N - SDM13 Bump Suffix for Boot loader fix for black screen.xlsm |  | PMT 2 |  |  |  | No | C14746464 | Cost Only to expedite suffix bump for boot loader update to prevent black screens | 4940 | No Impact | No Impact | Joel Turbiak (jturbia1) | 25CRF00392 |  | (Non-Disc) CRITICAL TO WARRANTY – CW
6 | U6XX - Safety Cert & Tread Label - PCA 2pgr - Vetted.xlsm | 25MY - U625 NA | PMT 1 | -0.02 |  |  | No | C14724397 | ADHESIVE MATERIAL CHANGE FROM RS-4253 (ADHESIVE S8015W - SUFFIX AA) TO RS-4254 (ADHESIVE S8015LW - SUFFIX AB). |  | - | - | Leandro Leal |  |  | (Disc) QUALITY ROBUSTNESS – QR | Program
6 | U6XX - Safety Cert & Tread Label - PCA 2pgr - Vetted.xlsm | 24MY - U611 NA | PMT 1 | -0.02 |  |  | No | C14724397 | ADHESIVE MATERIAL CHANGE FROM RS-4253 (ADHESIVE S8015W - SUFFIX AA) TO RS-4254 (ADHESIVE S8015LW - SUFFIX AB). |  | - | - | Leandro Leal |  | RU5A-1520472-AA, RU5A-1532-AA, RU5A-1520472-AB, RU5A-1532-AB | (Disc) QUALITY ROBUSTNESS – QR | Program
7 | U611 VISION SYSTEM AT CAP.xlsm | 25.5MY - U611 NA | PMT 3 |  |  | -14.12 | No | C14711053 | U611 25.5MY AIR SUSPENSION LINES MARKING UPDATE AND CAP VISION SYSTEM IMPLEMENET. |  |  |  | Oscar Jardón (ojardon) |  |  | (Non-Disc) CRITICAL TO WARRANTY – CW | Program
8 | 25CRF00390 - C14716423 U611 Cost only Update for LDM4.2.2 Rev3.xlsm | 24MY - U611 China | PMT 1 | -1.52 |  |  |  | C14716423 | Update cost for LDM4.2.2 |  |  |  | SRASHADO | 25CRF00390 |  | (Non-Disc) CRITICAL TO WARRANTY – CW
9 | 25CRF00390 - C14716423 U611 Cost only Update for LDM4.2.2 Rev3.xlsm | 24MY - U611 China | PMT 1 | -1.52 |  |  |  | C14716423 | Update cost for LDM4.2.2 |  |  |  | SRASHADO | 25CRF00390 |  | (Non-Disc) CRITICAL TO WARRANTY – CW
10 | 25CRF00390 - C14716423 U611 Cost only Update for LDM4.2.2 Rev3.xlsm | 24MY - U611 China | PMT 1 | -1.52 |  |  |  | C14716423 | Update cost for LDM4.2.2 |  |  |  | SRASHADO | 25CRF00390 |  | (Non-Disc) CRITICAL TO WARRANTY – CW